## Slide 1
Product Review Meeting
June 2025 – Presented by the Project Team
Eric Breighner
Project Manager & Lead Developer
Samuel Thomas
DevOps Engineer
Brian Stehle
QA & Website Development Lead
Olivia Martin
Data Specialist
Notes: Good morning everyone, and thank you for attending this stakeholder review meeting for the Silver Exposure Photography digital transformation project. My name is Eric Breighner, and I’m serving as the Project Manager and Lead Developer.
Before we begin, I’d like to introduce the rest of our project team. Samuel Thomas is our DevOps Engineer. He’s been responsible for ensuring smooth deployment and maintaining our infrastructure, including the server, networking equipment, and security protocols. Olivia Martin is our Data Specialist. She’s handled system documentation, gathered requirements, and coordinated vendor contracts throughout the project. And finally, Brian Stehle is our QA and Testing Lead. He’s also been developing the website’s front-end interface, using his design skills to bring the visual elements of the platform to life.
Each member of this team has played a vital role in shaping this transformation. We’ve all worked hard to build a system that’s technically strong, visually polished, and tailored specifically to Silver Exposure’s business needs. Today, we’re here to show you where the project stands at the 70% mark, and get your feedback before we move into the final phase.

## Slide 2
Meeting Objectives & Agenda
Objectives
Review current state of product
Confirm team/stakeholder alignment
Gather feedback for final 30%
Agenda
Project Overview
Live Demo
Progress Update
Budget Review
Stakeholder Input
Next Steps
Notes: The purpose of today’s meeting is to review the current state of the product, confirm alignment between our team and stakeholders, and gather feedback that will guide the final 30% of work. We’ll begin with a brief overview of the project and team, followed by a live demo of the completed features. After that, we’ll walk through progress visuals, technical updates, feedback we’ve already received, our budget status, and remaining tasks. Finally, we’ll open the floor for any key questions or decisions that need to be addressed before wrapping up with a look at next steps.

## Slide 3
Key Milestones Achieved
Project Status Overview
Progress
Budget
Spent $50,894.20
Total Budget: $72,706
Status: On Time/Under Budget
70%
Complete
Hardware
Installation
June 6
Wireframe
Review
June 25
Website
Development
75% Complete
Key Milestones Achieved
Notes: We’re currently about 70% complete with the Silver Exposure digital upgrade. Major infrastructure work is finished, and our website platform is roughly 75% developed. Our hardware installation was completed on schedule by June 6, and we recently conducted a successful wireframe review with stakeholders on June 25. We’ve spent about $50,894.20 of the allocated $72,706 budget and are on track to finish under budget and on time, with our final delivery set for July 15, 2025.

## Slide 4
Product is
70% complete,
Review focused
on remaining work.
Team and stakeholders aligned on progress and goals.
Final feedback needed, budget still on track for completion.
Notes: At this point in the presentation, we’ll shift into a live demo of the system. You’ll see the homepage, the photo gallery, the client login page, the integrated shopping cart, and the contact form in action. We’ll also preview the admin management interface, which is partially complete. As we go through the demo, we’ll highlight how these features support Silver Exposure’s business goals, including better customer access, streamlined ordering, and a modern, mobile-friendly interface. Known issues are minor, and most of them have already been fixed/resolved.

## Slide 5
What’s Done
Website 75%
Complete.
Hardware Fully Installed.
Stakeholder Feedback Addressed.
What’s Left
Admin Panel Final Build.
UAT & Stress Testing.
Documentation & Backups.
Final Delivery:
July19
Notes: Now that we’ve seen what’s already been built, let’s look at what’s left. The final 30% includes the completion of the admin panel, final usability testing, cloud and onsite backup validation, and documentation. Brian and I are finalizing the admin tools together, while Olivia is preparing user acceptance test planning and quality assurance documentation. No critical blockers remain at this point, and our team is confident in the final timeline.

## Slide 6
Key Technical Components
System Installation Summary
15 Dell workstations installed
HPE server with RAID (32+ GB RAM)
QNAP router/firewall with VLAN setup
Synology NAS + printer
Fully labeled and configured
Deployment led by Samuel Thomas(DevOps)
Notes: Much of the heavy lifting on the technical side has already been done. Between June 4 and June 6, we installed and configured 15 Dell office workstations, an enterprise-class HPE server with RAID redundancy, a QNAP router/firewall, and a Synology NAS and printer system. Everything was deployed efficiently, using VLAN tagging, static IP configuration, and full patch panel labeling based on our topology documentation. These installations were led by Samuel Thomas, our DevOps Engineer, who made sure everything came online smoothly with security protocols preloaded.

## Slide 7
Challenges & Lesson Learned
Tight two-month timeline
Integrating legacy tools
Stakeholder communication delays
Challenges
Lesson Learned
Better Project Planning and scoping
Importance of flexibility and support
Frequent progress updates are critical for success
Notes: While the project has gone well overall, we’ve learned a few valuable lessons along the way. For example, early testing revealed some confusion with the shop layout, so we redesigned it for better usability. Also, VLAN configuration had to be rescheduled outside business hours to avoid disrupting studio operations. These challenges didn’t derail the timeline, in fact, they led us to better workflows and tighter coordination. We see them as insights, not setbacks.

## Slide 8
Stakeholder Feedback & UI Changes
UI Improvements Based on Feedback
Stakeholder session held June 25
Larger Image previews added
Menu navigation improved on mobile
Color theme adjustments made
Positive feedback received
Notes: As you know, we held our stakeholder wireframe feedback session on June 25, and the response we received from you was very encouraging. You emphasized the importance of visual consistency, better gallery presentation, and simplified navigation. As a result, we made several updates, including larger image previews, improved color theming, and better menu responsiveness, especially on mobile devices. These changes are now in place and are helping to improve the overall experience for Silver Exposure’s clients.

## Slide 9
Budget Overview
Budget Allocation
$28,520 - Hardware
$11,669 – Hosting Tools
$10,705.20 – Labor Consulting
5% reserve buffer still intact
Project on track to finish under budget
Total Budget $72,706
Spent $50,894.20
Chart: 
| Hardware | Hosting & Tools | Labor & Consulting | Reserve
Budget | 0.32 | 0.14 | 0.28 | 0.05
Notes: Let’s take a quick look at the budget. Our total allocation was $72,706. So far, we’ve spent about $50,894.20, with $28,520 going toward hardware, $11,669 for web hosting and development tools, and $10,705.20 for labor and consulting. Thanks to early vendor coordination and bundled contracts, we avoided delays and surprise fees. We’ve also kept a 5% reserve buffer for any unexpected changes. At this point, we expect to finish the project under budget without sacrificing any major functionality.

## Slide 10
Stakeholder Input Needed
Outstanding Decisions
Deployment timeline
Hosting provider options
User training requirements
Post-launch support needs
Notes: Before we move toward final delivery, we want to make sure we’ve covered everything you need to see. Specifically, we’d like your input on the current version of the admin panel design. Are there any major changes still needed? Are there any essential features missing from your perspective? And are there any business priorities that haven’t been fully addressed? We’ll take note of any strategic adjustments, while smaller technical issues are already being tracked in a separate internal log.

## Slide 11
Remaining Task &Deadlines
Task Owner Due Date
Admin Panel Completion
Final Testing & UAT
Documentation & Backup
Final Review & Launch
Eric & Brian
Olivia & Brian
Olivia
Full Team
July 10
July 15
July 18
July 19
Notes: Here’s how we plan to wrap up the final phase of the project. The admin panel will be completed by Brian and me by July 8. Olivia and Brian will handle final testing and UAT by July 10. Olivia will also finalize the documentation and verify the cloud and onsite backup systems by July 12. Then we’ll reconvene for the final stakeholder review on July 13. Until then, we’ll continue providing regular updates and tracking every task to the finish line.

## Slide 12
Thank You
Silver Exposure
Notes: To close, I want to sincerely thank each of you for your continued trust, support, and feedback throughout this process. The Silver Exposure Photography transformation project has been an incredible collaboration. We’ve modernized outdated systems, added powerful new tools, and built a digital platform that truly reflects the studio’s professionalism. We’re excited to deliver the final version soon and we’re confident it will meet and hopefully exceed your expectations. Thank you again.